## Summary
ASG Stress Report Generation - Project Summary
| As-of date | 2026-10-13 | <- input (blue); drives Overdue / Due-in-7-days flags
By Workstream
| Workstream | Total | Complete | In Progress | Not Started | Blocked | Overdue | Avg % Complete
| UI | 5 | 1 | 2 | 2 | 0 | 1 | 26%
| Backend | 38 | 4 | 2 | 8 | 24 | 1 | 13.42%
| API | 7 | 1 | 4 | 2 | 0 | 2 | 44.29%
| LLM & RAG | 10 | 0 | 0 | 7 | 3 | 0 | 0%
| Testing & Release | 9 | 0 | 0 | 9 | 0 | 0 | 0%
| Total | 69 | 6 | 8 | 28 | 27 | 4 | 13.77%
By Owner
| Owner | Total | Complete | In Progress | Not Started | Blocked | Overdue
| Abhik | 12 | 2 | 8 | 2 | 0 | 4
| Srujan | 5 | 3 | 0 | 2 | 0 | 0
| Rajesh | 1 | 0 | 0 | 1 | 0 | 0
| Srujan, Rajesh, Abhik | 10 | 1 | 0 | 9 | 0 | 0
| Unassigned | 41 | 0 | 0 | 14 | 27 | 0
| Total | 69 | 6 | 8 | 28 | 27 | 4
| Check: owner total = workstream total | OK
Legend: blue = input/editable, green = linked from another sheet, black = formula. Colours in Status / Schedule Flag are conditional.
Task Origin & Section Coverage
| Item | Count
| Tasks from Project Plan | 54
| Tasks proposed from SRG Sections | 15
| AR sections (SRG Sections) | 14
| Sections where ASG and ART are NOT aligned | 5
| Sections covered only by proposed tasks | 3
| Sections with no tasks / missing LLM task | 0
Note on C3: Input. Set to 13-Oct-2026 (date of the screenshots). Replace with =TODAY() for a live view.

## Master Plan
ASG Stress Report Generation - Master Project Plan
Single source of truth (Project Plan tasks + tasks proposed from SRG Sections - see Origin column). Edit blue cells (Owner, Start, Finish, % Complete, Blocked?, Dependency, Notes). Status, Duration, Schedule Flag, workstream tabs and Summary update automatically. As-of date is set on Summary!C3.
ID | Workstream | Feature / Report Section | Task | Owner | Start | Finish | Duration (days) | % Complete | Blocked? | Status | Schedule Flag | Dependency / Blocker | Source Row | Notes | Origin
T-001 | UI | Project Setup | UI folder setup and Login | Abhik | 2026-09-21 | 2026-10-09 | 18 | 100% | No | Complete | Done |  | 2 |  | Project Plan
T-002 | UI | Header Section | UI design for collecting Header fields info (Engineer name, Date, Model, Report, Revision version) | Abhik | 2026-09-28 | 2026-10-23 | 25 | 10% | No | In Progress | On track |  | 6 | Date field added per SRG Sections (ART suggestion 8/10/26) | Project Plan
T-003 | UI | Revision Record Table | UI to collect Revision changes (Revision, Date, Change Description, Approvals) | Abhik | 2026-10-09 | 2026-10-23 | 14 | 20% | No | In Progress | On track |  | 10 | Finish date read as 23/16/2026 in source; assumed 23/10/2026. Fields per SRG Sections (first row auto-filled; rest from UI) | Project Plan
T-004 | UI | Component Description | UI to capture Program, Component, Loads | Abhik | 2026-09-21 | 2026-10-09 | 18 | 0% | No | Not Started | OVERDUE |  | 39 |  | Project Plan
T-005 | UI | FEM Description | UI for uploading BDF and DAT input files | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-19 | Proposed: input channel for BDF/DAT not specified in source - confirm | Proposed
T-006 | Backend | Project Setup | Postgres database setup and data model to store login info (local env) | Abhik | 2026-09-21 | 2026-10-09 | 18 | 90% | No | In Progress | OVERDUE |  | 3 |  | Project Plan
T-007 | Backend | Header Section | YAML to add Header section in AR | Srujan | 2026-09-28 | 2026-10-16 | 18 | 100% | No | Complete | Done |  | 8 |  | Project Plan
T-008 | Backend | Table of Contents | YAML to add TOC section in AR | Srujan | 2026-09-28 | 2026-10-01 | 3 | 100% | No | Complete | Done |  | 9 |  | Project Plan
T-009 | Backend | Revision Record Table | Data model for saving Revision history (only first revision auto-filled; later revisions manual entry) | Abhik | 2026-10-09 | 2026-10-23 | 14 | 20% | No | In Progress | On track |  | 12 | Finish date read as 23/16/2026 in source; assumed 23/10/2026 | Project Plan
T-010 | Backend | Revision Record Table | YAML to add Revision table to AR | Srujan | 2026-09-28 | 2026-10-16 | 18 | 100% | No | Complete | Done |  | 13 |  | Project Plan
T-011 | Backend | List of Parts | Automation to extract List of Parts from BOMSTR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | 31 |  | Project Plan
T-012 | Backend | List of Parts | Automation/OCR to extract List of Parts from Drawing documents | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | 32 | ART recommends BOMSTR instead: drawings only have high-level part numbers (no sub-parts) and OCR needs extra processing (8/10/26) | Project Plan
T-013 | Backend | List of Parts | Automation to download PDF from Teamcenter | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide API access to Teamcenter | 33 | Long-term per ART; Teamcenter API access currently unavailable (8/10/26) | Project Plan
T-014 | Backend | List of Parts | YAML to add List of Parts section in AR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | 34 |  | Project Plan
T-015 | Backend | Margin of Safety (MS) Summary | Automation to extract Location ID | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide Location ID for analysis (not feasible to extract from CATIA images) | 35 | Feature grouping inferred. CONFLICT: plan says not feasible from CATIA images; SRG Sections (8/10/26) says Location ID will come from CATIA image - confirm with ASG | Project Plan
T-016 | Backend | Margin of Safety (MS) Summary | Automation to extract Part Number, Material, Temp, Applied Condition/Load ID, Applied Load/Stress, Allowable Load/Stress, Failure Mode, MS | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to output Part Number, Material, Temp, Load ID, Applied/Allowable Load-Stress, Failure Mode, MS in Excel (confirmed in 5/10/26 meeting) | 36 | MS comes from one-stop stress tool Excel output | Project Plan
T-017 | Backend | Margin of Safety (MS) Summary | Automation to create MOS summary table | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to output Part Number, Material, Temp, Load ID, Applied/Allowable Load-Stress, Failure Mode, MS in Excel (confirmed in 5/10/26 meeting) | 37 |  | Project Plan
T-018 | Backend | Margin of Safety (MS) Summary | YAML to add MOS Summary section in AR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to output Part Number, Material, Temp, Load ID, Applied/Allowable Load-Stress, Failure Mode, MS in Excel (confirmed in 5/10/26 meeting) | 38 |  | Project Plan
T-019 | Backend | Component Description | Automation to merge UI and RAG data | Abhik | 2026-10-09 | 2026-10-23 | 14 | 0% | No | Not Started | On track |  | 41 |  | Project Plan
T-020 | Backend | Component Description | Add images to Component Description | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide Images | 42 |  | Project Plan
T-021 | Backend | Component Description | YAML to add Component Description section | Srujan | 2026-10-09 | 2026-10-23 | 14 | 0% | No | Not Started | On track |  | 43 |  | Project Plan
T-022 | Backend | Loads Section | Automation to get Loads information from One Stop Stress tool | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Loads | 45 | Dependency cell showed 'sr' in source; inferred from adjacent rows | Project Plan
T-023 | Backend | Loads Section | YAML to add Loads section in AR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Loads | 46 |  | Project Plan
T-024 | Backend | Loads Section | Add images to Loads section | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide Images | 47 |  | Project Plan
T-025 | Backend | Static Analysis Section | Automation to get Static Analysis from One Stop Stress tool | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Static Analysis | 49 |  | Project Plan
T-026 | Backend | Static Analysis Section | YAML to add Static Analysis section in AR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Static Analysis | 50 |  | Project Plan
T-027 | Backend | Static Analysis Section | Add images to Static Analysis section | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide Images | 51 |  | Project Plan
T-028 | Backend | Materials (Metallic) Section | Automation to extract List of Parts from BOMSTR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | 53 |  | Project Plan
T-029 | Backend | Materials (Metallic) Section | Automation/OCR to extract List of Parts from Drawing documents | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | 54 | ART recommends BOMSTR instead: drawings only have high-level part numbers (no sub-parts) and OCR needs extra processing (8/10/26) | Project Plan
T-030 | Backend | Materials (Metallic) Section | Automation to download PDF from Teamcenter | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide API access to Teamcenter | 55 | Long-term per ART; Teamcenter API access currently unavailable (8/10/26) | Project Plan
T-031 | Backend | Materials (Metallic) Section | Add images to Materials section | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide Images | 56 |  | Project Plan
T-032 | Backend | Materials (Metallic) Section | YAML to add Materials section in AR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | 57 |  | Project Plan
T-033 | Backend | References Section | Automation for generating Reference section from previous ARs | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide list of ESOMS to component Mapping | 58 | ASG agreed (9/7/26) to provide Excel of ESOMs used in component - not received yet | Project Plan
T-034 | Backend | References Section | YAML to add Reference section in AR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide list of ESOMS to component Mapping | 59 |  | Project Plan
T-035 | Backend | Fan Cowl AR - Release & Testing | Generate Report for Fan Cowl AR | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 100% | No | Complete | Done |  | 60 | Shown as 100% in source although finish date is 2/12/2026 - please verify | Project Plan
T-036 | Backend | Scope Section | YAML to add Scope section in AR | Unassigned |  |  |  | 0% | No | Not Started | No dates | UI to capture Program, Component, Loads | SRG-12 | Proposed from SRG Sections row 12 (Scope not in original plan) | Proposed
T-037 | Backend | Analysis Checklist | Automation to build Analysis Checklist from Failure Mode Matrix Excel | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-11 | Proposed. SRG says ART already developed a solution - confirm status / % done | Proposed
T-038 | Backend | Analysis Checklist | YAML to add Analysis Checklist section in AR | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-11 | Proposed from SRG Sections row 11 (not in original plan) | Proposed
T-039 | Backend | FEM Description | Automation to parse BDF/DAT (component name, element/property/material type, material description, solver, solution type/description, total and excluded elements) | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-19 | Proposed from SRG Sections row 19 (FEM not in original plan) | Proposed
T-040 | Backend | FEM Description | YAML to add FEM Description section in AR | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-19 | Proposed from SRG Sections row 19 | Proposed
T-041 | Backend | FEM Description | FEM subsections (Model Setup, Boundary Conditions, Results) and images | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to review FEM requirements and clarify which FEM subsections to include (agreed 8/10/26) | SRG-19 | Subsections inconsistent across previous ARs (ART observation 8/10/26) | Proposed
T-042 | Backend | Appendix | Automation to populate Appendix from ASG-provided folder | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to provide folder with Appendix files (agreed 9/7/26) | SRG-21 | Assumed folder not yet delivered - confirm | Proposed
T-043 | Backend | Appendix | YAML to add Appendix section in AR | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-21 | Proposed from SRG Sections row 21 (Appendix not in original plan) | Proposed
T-044 | API | Project Setup | API for login page | Abhik | 2026-09-21 | 2026-10-09 | 18 | 90% | No | In Progress | OVERDUE |  | 4 |  | Project Plan
T-045 | API | Project Setup | API layer folder setup (local env) | Abhik | 2026-09-21 | 2026-10-09 | 18 | 90% | No | In Progress | OVERDUE |  | 5 |  | Project Plan
T-046 | API | Header Section | API design to add Header fields to Word template | Abhik | 2026-09-28 | 2026-10-23 | 25 | 10% | No | In Progress | On track |  | 7 |  | Project Plan
T-047 | API | Revision Record Table | API design to add Revision fields to table | Abhik | 2026-10-09 | 2026-10-23 | 14 | 20% | No | In Progress | On track |  | 11 | Finish date read as 23/16/2026 in source; assumed 23/10/2026 | Project Plan
T-048 | API | Analysis Checklist | API for reading Failure Mode Matrix spreadsheet | Abhik | 2026-09-21 | 2026-10-09 | 18 | 100% | No | Complete | Done | Not considered - previous ARs will be used | 14 | Descoped per project plan note, BUT SRG Sections says ART developed a Failure Mode Matrix based solution for the Analysis Checklist - reconcile | Project Plan
T-049 | API | Scope Section | API to store/serve Program, Component, Loads inputs (shared by Scope and Component Description) | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-12 | Proposed: UI capture task exists but no matching API task | Proposed
T-050 | API | FEM Description | API to receive BDF/DAT files and return extracted FEM attributes | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-19 | Proposed: input channel for BDF/DAT not specified in source - confirm | Proposed
T-051 | LLM & RAG | Component Description | RAG to populate Connection Type, Load Path | Rajesh | 2026-10-09 | 2026-10-23 | 14 | 0% | No | Not Started | On track |  | 40 |  | Project Plan
T-052 | LLM & RAG | Component Description | LLM generation for Component Description | Srujan | 2026-10-09 | 2026-10-23 | 14 | 0% | No | Not Started | On track |  | 44 |  | Project Plan
T-053 | LLM & RAG | Loads Section | LLM generation for Loads section in AR | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Loads | 48 |  | Project Plan
T-054 | LLM & RAG | Static Analysis Section | LLM generation for Static Analysis section in AR (step-by-step calculation paragraphs) | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Static Analysis | 52 |  | Project Plan
T-055 | LLM & RAG | Fan Cowl AR - Release & Testing | RAG pipeline testing | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 67 |  | Project Plan
T-056 | LLM & RAG | Fan Cowl AR - Release & Testing | Testing LLM-generated text / RAG pipeline | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 68 |  | Project Plan
T-057 | LLM & RAG | Environment & RAG Setup | RAG pipeline setup | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | 72 | Heading only in source (no tasks/dates) - placeholder, please break down | Project Plan
T-058 | LLM & RAG | Scope Section | LLM generation for Scope paragraph (from Program, Component, Loads) | Unassigned |  |  |  | 0% | No | Not Started | No dates | UI to capture Program, Component, Loads | SRG-12 | Proposed from SRG Sections row 12 (AI = Yes) | Proposed
T-059 | LLM & RAG | FEM Description | LLM generation for FEM Description (single paragraph from BDF/DAT attributes) | Unassigned |  |  |  | 0% | No | Not Started | No dates | Automation to parse BDF/DAT | SRG-19 | ASG suggested single paragraph (9/7/26) | Proposed
T-060 | LLM & RAG | Materials (Metallic) Section | LLM generation for Materials section | Unassigned |  |  |  | 0% | Yes | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | SRG-17 | Proposed: SRG marks Materials as AI = Yes but plan had no LLM task. Billet Size remains a limitation with BOMSTR | Proposed
T-061 | Testing & Release | Fan Cowl AR - Release & Testing | Deployment of code to pre-prod server | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 61 |  | Project Plan
T-062 | Testing & Release | Fan Cowl AR - Release & Testing | Unit testing | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 62 |  | Project Plan
T-063 | Testing & Release | Fan Cowl AR - Release & Testing | CI/CD pipeline | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 63 |  | Project Plan
T-064 | Testing & Release | Fan Cowl AR - Release & Testing | Documentation | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 64 |  | Project Plan
T-065 | Testing & Release | Fan Cowl AR - Release & Testing | Monitoring and Dashboard | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 65 |  | Project Plan
T-066 | Testing & Release | Fan Cowl AR - Release & Testing | Integration testing | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 66 |  | Project Plan
T-067 | Testing & Release | Fan Cowl AR - Release & Testing | Testing end-to-end program | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 54 | 0% | No | Not Started | On track |  | 69 |  | Project Plan
T-068 | Testing & Release | Environment & RAG Setup | Environment setup | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | 70 | Heading only in source (no tasks/dates) - placeholder, please break down | Project Plan
T-069 | Testing & Release | Fan Cowl AR - Release & Testing | Validate generated report for all 17 Fan Cowl components | Unassigned |  |  |  | 0% | No | Not Started | No dates |  | SRG-3 | Proposed: SRG Sections lists 17 components | Proposed

## UI Tasks
UI Tasks |  |  |  |  | Tasks | 5 | Avg % Done | 26%
Linked to 'Master Plan' - edit there, this tab updates automatically.
ID | Feature / Report Section | Task | Owner | Start | Finish | % Complete | Status | Schedule Flag | Dependency / Blocker | Origin
T-001 | Project Setup | UI folder setup and Login | Abhik | 2026-09-21 | 2026-10-09 | 100% | Complete | Done |  | Project Plan
T-002 | Header Section | UI design for collecting Header fields info (Engineer name, Date, Model, Report, Revision version) | Abhik | 2026-09-28 | 2026-10-23 | 10% | In Progress | On track |  | Project Plan
T-003 | Revision Record Table | UI to collect Revision changes (Revision, Date, Change Description, Approvals) | Abhik | 2026-10-09 | 2026-10-23 | 20% | In Progress | On track |  | Project Plan
T-004 | Component Description | UI to capture Program, Component, Loads | Abhik | 2026-09-21 | 2026-10-09 | 0% | Not Started | OVERDUE |  | Project Plan
T-005 | FEM Description | UI for uploading BDF and DAT input files | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed

## Backend Tasks
Backend Tasks |  |  |  |  | Tasks | 38 | Avg % Done | 13.42%
Linked to 'Master Plan' - edit there, this tab updates automatically.
ID | Feature / Report Section | Task | Owner | Start | Finish | % Complete | Status | Schedule Flag | Dependency / Blocker | Origin
T-006 | Project Setup | Postgres database setup and data model to store login info (local env) | Abhik | 2026-09-21 | 2026-10-09 | 90% | In Progress | OVERDUE |  | Project Plan
T-007 | Header Section | YAML to add Header section in AR | Srujan | 2026-09-28 | 2026-10-16 | 100% | Complete | Done |  | Project Plan
T-008 | Table of Contents | YAML to add TOC section in AR | Srujan | 2026-09-28 | 2026-10-01 | 100% | Complete | Done |  | Project Plan
T-009 | Revision Record Table | Data model for saving Revision history (only first revision auto-filled; later revisions manual entry) | Abhik | 2026-10-09 | 2026-10-23 | 20% | In Progress | On track |  | Project Plan
T-010 | Revision Record Table | YAML to add Revision table to AR | Srujan | 2026-09-28 | 2026-10-16 | 100% | Complete | Done |  | Project Plan
T-011 | List of Parts | Automation to extract List of Parts from BOMSTR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | Project Plan
T-012 | List of Parts | Automation/OCR to extract List of Parts from Drawing documents | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | Project Plan
T-013 | List of Parts | Automation to download PDF from Teamcenter | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide API access to Teamcenter | Project Plan
T-014 | List of Parts | YAML to add List of Parts section in AR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | Project Plan
T-015 | Margin of Safety (MS) Summary | Automation to extract Location ID | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide Location ID for analysis (not feasible to extract from CATIA images) | Project Plan
T-016 | Margin of Safety (MS) Summary | Automation to extract Part Number, Material, Temp, Applied Condition/Load ID, Applied Load/Stress, Allowable Load/Stress, Failure Mode, MS | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to output Part Number, Material, Temp, Load ID, Applied/Allowable Load-Stress, Failure Mode, MS in Excel (confirmed in 5/10/26 meeting) | Project Plan
T-017 | Margin of Safety (MS) Summary | Automation to create MOS summary table | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to output Part Number, Material, Temp, Load ID, Applied/Allowable Load-Stress, Failure Mode, MS in Excel (confirmed in 5/10/26 meeting) | Project Plan
T-018 | Margin of Safety (MS) Summary | YAML to add MOS Summary section in AR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to output Part Number, Material, Temp, Load ID, Applied/Allowable Load-Stress, Failure Mode, MS in Excel (confirmed in 5/10/26 meeting) | Project Plan
T-019 | Component Description | Automation to merge UI and RAG data | Abhik | 2026-10-09 | 2026-10-23 | 0% | Not Started | On track |  | Project Plan
T-020 | Component Description | Add images to Component Description | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide Images | Project Plan
T-021 | Component Description | YAML to add Component Description section | Srujan | 2026-10-09 | 2026-10-23 | 0% | Not Started | On track |  | Project Plan
T-022 | Loads Section | Automation to get Loads information from One Stop Stress tool | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Loads | Project Plan
T-023 | Loads Section | YAML to add Loads section in AR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Loads | Project Plan
T-024 | Loads Section | Add images to Loads section | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide Images | Project Plan
T-025 | Static Analysis Section | Automation to get Static Analysis from One Stop Stress tool | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Static Analysis | Project Plan
T-026 | Static Analysis Section | YAML to add Static Analysis section in AR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Static Analysis | Project Plan
T-027 | Static Analysis Section | Add images to Static Analysis section | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide Images | Project Plan
T-028 | Materials (Metallic) Section | Automation to extract List of Parts from BOMSTR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | Project Plan
T-029 | Materials (Metallic) Section | Automation/OCR to extract List of Parts from Drawing documents | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | Project Plan
T-030 | Materials (Metallic) Section | Automation to download PDF from Teamcenter | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide API access to Teamcenter | Project Plan
T-031 | Materials (Metallic) Section | Add images to Materials section | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide Images | Project Plan
T-032 | Materials (Metallic) Section | YAML to add Materials section in AR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | Project Plan
T-033 | References Section | Automation for generating Reference section from previous ARs | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide list of ESOMS to component Mapping | Project Plan
T-034 | References Section | YAML to add Reference section in AR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide list of ESOMS to component Mapping | Project Plan
T-035 | Fan Cowl AR - Release & Testing | Generate Report for Fan Cowl AR | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 100% | Complete | Done |  | Project Plan
T-036 | Scope Section | YAML to add Scope section in AR | Unassigned |  |  | 0% | Not Started | No dates | UI to capture Program, Component, Loads | Proposed
T-037 | Analysis Checklist | Automation to build Analysis Checklist from Failure Mode Matrix Excel | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed
T-038 | Analysis Checklist | YAML to add Analysis Checklist section in AR | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed
T-039 | FEM Description | Automation to parse BDF/DAT (component name, element/property/material type, material description, solver, solution type/description, total and excluded elements) | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed
T-040 | FEM Description | YAML to add FEM Description section in AR | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed
T-041 | FEM Description | FEM subsections (Model Setup, Boundary Conditions, Results) and images | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to review FEM requirements and clarify which FEM subsections to include (agreed 8/10/26) | Proposed
T-042 | Appendix | Automation to populate Appendix from ASG-provided folder | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to provide folder with Appendix files (agreed 9/7/26) | Proposed
T-043 | Appendix | YAML to add Appendix section in AR | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed

## API Tasks
API Tasks |  |  |  |  | Tasks | 7 | Avg % Done | 44.29%
Linked to 'Master Plan' - edit there, this tab updates automatically.
ID | Feature / Report Section | Task | Owner | Start | Finish | % Complete | Status | Schedule Flag | Dependency / Blocker | Origin
T-044 | Project Setup | API for login page | Abhik | 2026-09-21 | 2026-10-09 | 90% | In Progress | OVERDUE |  | Project Plan
T-045 | Project Setup | API layer folder setup (local env) | Abhik | 2026-09-21 | 2026-10-09 | 90% | In Progress | OVERDUE |  | Project Plan
T-046 | Header Section | API design to add Header fields to Word template | Abhik | 2026-09-28 | 2026-10-23 | 10% | In Progress | On track |  | Project Plan
T-047 | Revision Record Table | API design to add Revision fields to table | Abhik | 2026-10-09 | 2026-10-23 | 20% | In Progress | On track |  | Project Plan
T-048 | Analysis Checklist | API for reading Failure Mode Matrix spreadsheet | Abhik | 2026-09-21 | 2026-10-09 | 100% | Complete | Done | Not considered - previous ARs will be used | Project Plan
T-049 | Scope Section | API to store/serve Program, Component, Loads inputs (shared by Scope and Component Description) | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed
T-050 | FEM Description | API to receive BDF/DAT files and return extracted FEM attributes | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed

## LLM & RAG Tasks
LLM & RAG Tasks |  |  |  |  | Tasks | 10 | Avg % Done | 0%
Linked to 'Master Plan' - edit there, this tab updates automatically.
ID | Feature / Report Section | Task | Owner | Start | Finish | % Complete | Status | Schedule Flag | Dependency / Blocker | Origin
T-051 | Component Description | RAG to populate Connection Type, Load Path | Rajesh | 2026-10-09 | 2026-10-23 | 0% | Not Started | On track |  | Project Plan
T-052 | Component Description | LLM generation for Component Description | Srujan | 2026-10-09 | 2026-10-23 | 0% | Not Started | On track |  | Project Plan
T-053 | Loads Section | LLM generation for Loads section in AR | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Loads | Project Plan
T-054 | Static Analysis Section | LLM generation for Static Analysis section in AR (step-by-step calculation paragraphs) | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team One Stop Stress tool not ready yet for Static Analysis | Project Plan
T-055 | Fan Cowl AR - Release & Testing | RAG pipeline testing | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-056 | Fan Cowl AR - Release & Testing | Testing LLM-generated text / RAG pipeline | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-057 | Environment & RAG Setup | RAG pipeline setup | Unassigned |  |  | 0% | Not Started | No dates |  | Project Plan
T-058 | Scope Section | LLM generation for Scope paragraph (from Program, Component, Loads) | Unassigned |  |  | 0% | Not Started | No dates | UI to capture Program, Component, Loads | Proposed
T-059 | FEM Description | LLM generation for FEM Description (single paragraph from BDF/DAT attributes) | Unassigned |  |  | 0% | Not Started | No dates | Automation to parse BDF/DAT | Proposed
T-060 | Materials (Metallic) Section | LLM generation for Materials section | Unassigned |  |  | 0% | Blocked | Blocked | ASG Team to confirm if BOMSTR or Drawing PDF? | Proposed

## Testing & Release
Testing & Release Tasks |  |  |  |  | Tasks | 9 | Avg % Done | 0%
Linked to 'Master Plan' - edit there, this tab updates automatically.
ID | Feature / Report Section | Task | Owner | Start | Finish | % Complete | Status | Schedule Flag | Dependency / Blocker | Origin
T-061 | Fan Cowl AR - Release & Testing | Deployment of code to pre-prod server | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-062 | Fan Cowl AR - Release & Testing | Unit testing | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-063 | Fan Cowl AR - Release & Testing | CI/CD pipeline | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-064 | Fan Cowl AR - Release & Testing | Documentation | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-065 | Fan Cowl AR - Release & Testing | Monitoring and Dashboard | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-066 | Fan Cowl AR - Release & Testing | Integration testing | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-067 | Fan Cowl AR - Release & Testing | Testing end-to-end program | Srujan, Rajesh, Abhik | 2026-10-09 | 2026-12-02 | 0% | Not Started | On track |  | Project Plan
T-068 | Environment & RAG Setup | Environment setup | Unassigned |  |  | 0% | Not Started | No dates |  | Project Plan
T-069 | Fan Cowl AR - Release & Testing | Validate generated report for all 17 Fan Cowl components | Unassigned |  |  | 0% | Not Started | No dates |  | Proposed

## Blockers
Blockers & External Dependencies
Counts are live (matched to Master Plan column M). 'Suggested next step' is a recommendation, not from the source sheet.
# | Dependency / Blocker | Needed From | Blocked Tasks | Affected Features | Suggested Next Step
1 | ASG Team to confirm if BOMSTR or Drawing PDF? | ASG Team | 7 | List of Parts, Materials | ART recommends BOMSTR (drawings lack sub-parts). Get Design team written confirmation; if BOMSTR is approved, the OCR tasks can be dropped.
2 | ASG Team to provide API access to Teamcenter | ASG Team | 2 | List of Parts, Materials | SRG Sections says API access is unavailable and MDX / Material DB access was denied. Treat as long-term; use BOMSTR as workaround.
3 | ASG Team to provide Location ID for analysis (not feasible to extract from CATIA images) | ASG Team | 1 | Margin of Safety Summary | Conflicting notes (plan: not feasible from CATIA; SRG 8/10/26: from CATIA image). Get a single answer; prefer a Location ID column in the ASG Excel.
4 | ASG Team to output Part Number, Material, Temp, Load ID, Applied/Allowable Load-Stress, Failure Mode, MS in Excel (confirmed in 5/10/26 meeting) | ASG Team | 3 | Margin of Safety Summary | Obtain the Excel output template/sample from ASG and build parser against it.
5 | ASG Team to provide Images | ASG Team | 4 | Component Description, Loads, Static Analysis, Materials | Agree image format/naming and a hand-off location so the 'Add images' tasks can be done in one batch.
6 | ASG Team One Stop Stress tool not ready yet for Loads | ASG Team | 3 | Loads Section | Request ETA for one-stop stress tool Loads output; use a mock JSON to unblock YAML/LLM work.
7 | ASG Team One Stop Stress tool not ready yet for Static Analysis | ASG Team | 3 | Static Analysis Section | Request ETA for Static Analysis output; use a mock payload to unblock YAML/LLM work.
8 | ASG Team to provide list of ESOMS to component Mapping | ASG Team | 2 | References Section | Request ESOMS-to-component mapping file (agreed 9/7/26, not received yet).
9 | ASG Team to review FEM requirements and clarify which FEM subsections to include (agreed 8/10/26) | ASG Team | 1 | FEM Description | Ask ASG to confirm which FEM subsections are required; single-paragraph FEM description can proceed meanwhile.
10 | ASG Team to provide folder with Appendix files (agreed 9/7/26) | ASG Team | 1 | Appendix | Request the Appendix files folder (agreed 9/7/26).
|  | Total | 27
Total can exceed the number of blocked tasks only if a task lists more than one blocker (none currently).

## Sections Register
AR Sections Register (from SRG Sections.xlsx) vs Plan Coverage
Project description | Automated tool that generates standardized, professional engineering stress analysis reports for Fancowl Static Analysis.
Fan Cowl AR components | 17: FC_RH_PANEL, FC_LH_PANEL, FC_RH_LONGERON, FC_LH_LONGERON, FC_HINGE_1, FC_HINGE_2, FC_HINGE_3, FC_HINGE_BEAM, FC_LATCH_KEEPER_1, FC_LATCH_KEEPER_2, FC_LATCH_KEEPER_3, PIVOT_BKT, FC_DRAINAGE_PLATE, FC_STRAKE, FC_PROX_SENSOR_BKT, FC_AXIAL_LOCATOR, FC_OTAD
Sections in AR | 14
Coverage / counts below are live formulas against Master Plan. Text columns are summarised from the source sheet.
Row | Section | LLM Used? | ASG Remarks (summary) | ART Short-term / Workaround | ART Long-term | ASG-ART Aligned? | Plan Feature | Plan Tasks | LLM & RAG Tasks | Avg % Done | Blocked Tasks | Coverage Check
8 | Header | No | Based on ASG-provided A320 NEO template: Engineer Name, Model, Report, Revision Version. | ASG template is the standard; UI captures Engineer Name, Date, Model, Report, Revision Version and fills the template header. | - | Yes | Header Section | 3 | 0 | 40% | 0 | Covered
9 | Table of Contents | No | List of all sections, tables and figures in the report. | Generate from finalized report structure; update automatically when content changes. | - | Yes | Table of Contents | 1 | 0 | 100% | 0 | Covered
10 | Revision Record | No | Captures revision history and relevant changes. | First row auto-filled; Revision, Date, Change Description and Approvals entered in the UI. | Track all revisions of LLM text/responses/images, keep version history, auto-generate change descriptions via semantic similarity / text-diff (revisit in 2027). | Yes | Revision Record Table | 4 | 0 | 40% | 0 | Covered
11 | Analysis Checklist | No | ASG agreed to provide all previously available AR checklists for reference. | Use the Failure Mode Matrix Excel shared by ASG as the primary reference. | - | Yes | Analysis Checklist | 3 | 0 | 33.33% | 0 | Covered
12 | Scope | Yes | Program, component, loads captured from UI; LLM generates the scope paragraph. | Proceed with UI-based input collection and LLM generation. | - | Yes | Scope Section | 3 | 1 | 0% | 0 | Proposed only
13 | Margin of Safety Summary | No | ASG to provide OneStopStressTool Excel: Part Number, Material, Temp, Applied Condition/Load ID, Applied/Allowable Load-Stress, Failure Mode, MS, Location ID. | Proceed once tool output is provided; confirm Location ID requirement with ASG. | - | Yes | Margin of Safety (MS) Summary | 4 | 0 | 0% | 4 | Covered
14 | List of Parts Covered | No | BOMSTR and drawing documents considered; BOMSTR has needed part/material info except Billet Size. | Use BOMSTR as primary source (workaround until Teamcenter API access). | Download drawing PDFs from Teamcenter to extract the parts list. | No | List of Parts | 4 | 0 | 0% | 4 | Covered
15 | Component Description | Yes | Covers Program, Component, Loads, Material, Connection Type, Load Path. Material from BOMSTR/drawings; RAG supports Connection Type and Load Path. | BOMSTR as primary source; finalize reference sources for Connection Type, Load Path and images. | Download drawing PDFs from Teamcenter for material info; MDX / Material Database access denied by ASG. | No | Component Description | 6 | 2 | 0% | 1 | Covered
16 | References | No | ASG confirmed a folder with files for the References table will be provided. | Extract references from previous AR. | - | No | References Section | 2 | 0 | 0% | 2 | Covered
17 | Materials | Yes | BOMSTR and drawing documents considered; BOMSTR has needed info except Billet Size. | Use BOMSTR as primary source; Billet Size remains a limitation until a source / Teamcenter access exists. | Download drawing PDFs from Teamcenter; MDX / Material Database access denied by ASG. | No | Materials (Metallic) Section | 6 | 1 | 0% | 6 | Covered
18 | Loads | Yes | Depends on load data generated by OneStopStressTool. | Proceed once load data is received and validated. | - | Yes | Loads Section | 4 | 1 | 0% | 4 | Covered
19 | FEM Description | Yes | BDF/DAT files used to extract component name, element/property/material type, material description, solver, solution type/description, total and excluded elements; other sources needed for Model Setup, Boundary Conditions, images. | Use extracted BDF/DAT info as LLM input; identify and finalize sources for Model Setup, Boundary Conditions, images. | - | No | FEM Description | 6 | 1 | 0% | 1 | Proposed only
20 | Static Analysis | Yes | Depends on analysis results from OneStopStressTool. | Proceed once results are available and validated. | - | Yes | Static Analysis Section | 4 | 1 | 0% | 4 | Covered
21 | Appendix | No | ASG confirmed a folder with the Appendix files will be provided. | Use ASG-provided files to populate the Appendix; keep the agreed report structure. | - | Yes | Appendix | 2 | 0 | 0% | 1 | Proposed only
Row = row number in SRG Sections.xlsx. ASG-ART Aligned? = 'No' means requirements/data source not yet agreed (risk to the plan).

## Decision Log
Decision & Meeting Log (from SRG Sections 'Scope Changes / Meeting Points')
Dates kept exactly as written in the source (dd/mm/yy). Plan impact column is my interpretation.
Date | Section | Raised By | Decision / Observation | Plan Impact
9/7/26 | Header | ASG | Provided template; agreed manual entry of Engineer Name, Model, Report, Revision Version. | Superseded by 8/10/26 UI approach.
8/10/26 | Header | ART | Suggested capturing Engineer Name, Date, Model, Report, Revision Version in the UI to remove manual entry in the AR. | UI + API header tasks (Date field added).
9/7/26 | Revision Record | ASG | Suggested Revision record is manual entry. | Superseded by 8/10/26.
8/10/26 | Revision Record | ART | Auto-populate only the first row of the Revision Record in 2026; track complete revisions via version control and store LLM paragraphs in a DB - full tracking to be revisited in 2027. | 2026 scope = first-row auto-fill + UI entry. Full tracking is 2027 backlog.
9/7/26 | Analysis Checklist | ASG | Suggested using the Failure Mode Matrix; ART developed a solution based on this approach. | Analysis Checklist tasks proposed; reconcile with descoped 'Failure Mode Matrix' API task.
(date not visible) | Analysis Checklist | ASG | Provided an Excel file containing the analysis checklist for Fancowl Static Analysis. | Input available for checklist automation.
1/10/26 | Margin of Safety Summary | ASG | Suggested using OneStop Stress to create the MOS summary table. | MS tasks depend on OneStopStressTool Excel.
8/10/26 | Margin of Safety Summary | ASG | Agreed to provide analysis in Excel but it will take time - activity on hold. Location ID will come from the CATIA image. | MS tasks stay Blocked. Conflicts with plan note that Location ID cannot be extracted from CATIA images.
9/7/26 | Component Description | ASG | Should cover Program, Component, Loads, Material; Connection Type and Load Path to be identified from previous ARs. | RAG task for Connection Type / Load Path.
8/10/26 | Component Description / Materials / List of Parts | ASG / ART | ASG suggested extracting part list/material from drawing PDFs, but drawings only have high-level part numbers (no sub-parts), Teamcenter API access is unavailable and OCR would need extra processing. ART suggested the BOMSTR Excel (part numbers, sub-parts, materials). Design team confirmation needed. | BOMSTR is the proposed primary source; OCR / Teamcenter tasks become long-term.
8/10/26 | Materials / Component Description | ASG | Access to Material Data Digitiser (MDX) and Material Database was requested but denied; ASG said it would not be useful. | No MDX / Material DB integration in plan. Billet Size remains a limitation.
9/7/26 | Component Description | ASG | ASG also needs to identify the images to be included. | Image dependency.
9/7/26 | References | ASG | Agreed to provide an Excel file containing the ESOMs used in the component; file not received yet. | References tasks Blocked.
9/7/26 | Loads | ASG | Still working on the One-Stop Stress Tool; not ready to provide Loads data. Section on hold. | Loads tasks Blocked.
9/7/26 | FEM Description | ASG | Suggested a single paragraph describing the FEM using solver, element type, material type, property type, solution type, component name, total/excluded elements, material description, solution description. | FEM paragraph tasks added (not in original plan).
8/10/26 | FEM Description | ART | FEM subsections are inconsistent across ARs (Model Setup, Results, Boundary Conditions...). Clarification needed; ASG agreed to review and get back. | FEM subsections task Blocked.
9/7/26 | Static Analysis | ASG | Still working on the One-Stop Stress Tool; section on hold. | Static Analysis tasks Blocked.
9/7/26 | Appendix | ASG | Agreed to provide a folder containing all files for the Appendix. | Appendix tasks added (not in original plan).
5/10/26 | Margin of Safety Summary | ASG | (From project plan) ASG confirmed they will output the MS data in an Excel file. | Input format agreed; delivery date not given.

## Notes
Assumptions, Gaps & Classification Rules
# | Topic | Detail
1 | Source | Built from 7 screenshots of the 'Project Plan' sheet (SharePoint, Sheet1). Dates are dd/mm/yyyy.
2 | GAP - rows 15-30 | Not visible in any screenshot (row 14 is cut off at the bottom of image 1; row 31 starts image 4). Not included. Send those rows to add them.
3 | Workstream rules | UI = screens/forms the user sees. API = endpoints/contracts exposed to the UI or other systems. Backend = data models, DB, YAML section definitions, extraction/OCR/merge automation, Teamcenter downloads, report generation. LLM & RAG = RAG retrieval/pipeline and LLM text generation (and their testing). Testing & Release = added 5th bucket for deployment, CI/CD, monitoring, documentation, unit/integration/E2E testing and environment setup.
4 | Judgement calls | 'YAML to add ... section in AR' tasks classed as Backend. 'Automation to download PDF from Teamcenter' classed as Backend (integration). 'Automation to merge UI and RAG data' classed as Backend. Change any in Master Plan column B.
5 | Date typo | Rows 10-12 Finish read as 23/16/2026 (invalid); assumed 23/10/2026.
6 | Name spelling | Source shows both 'Abihik' and 'Abhik'; normalised to 'Abhik'.
7 | Row 14 / rows 35-36 | Feature labels not visible. Row 14 grouped as 'Failure Mode Matrix' and marked descoped (source dependency note: previous ARs will be used). Rows 35-36 grouped under Margin of Safety (MS) Summary.
8 | Row 45 dependency | Source cell showed 'sr'; replaced with the same One Stop Stress / Loads dependency as rows 46 and 48.
9 | Row 60 | 'Generate Report for Fan Cowl AR' is 100% in source although finish is 2/12/2026 - please verify.
10 | Rows 70 / 72 | 'Environment setup' and 'RAG pipeline Setup' were headings with no tasks or dates - added as placeholders (Unassigned) for you to break down.
11 | SRG Sections (2nd upload) | Added from SRG Sections.xlsx (Sheet3, rows 8-21 visible): Sections Register + Decision Log tabs, 15 proposed tasks (Origin = Proposed, Unassigned, no dates - please assign and date them), and updated notes on existing tasks.
12 | Plan gaps found | Sections in SRG but missing from the original plan: Scope, Analysis Checklist, FEM Description, Appendix. Materials is marked AI = Yes but had no LLM task. No API task existed for Program/Component/Loads capture.
13 | Conflicts to resolve | (1) Location ID: plan says not feasible from CATIA images; SRG (8/10/26) says it will come from the CATIA image. (2) Failure Mode Matrix: plan descoped the API (use previous ARs); SRG says ART built a solution on the Failure Mode Matrix. (3) Teamcenter API: plan lists it as an ASG dependency; SRG says access is unavailable.
14 | Alignment column | ASG-ART alignment values were read from bottom-aligned cells in angled photos; the Component Description value was only partly visible. Please verify. Rows 1-7 and 22+ of SRG Sections were not fully visible.
15 | Dates in Decision Log | Kept as written (dd/mm/yy), e.g. 9/7/26 = 9 July 2026, 8/10/26 = 8 Oct 2026, consistent with the plan's dd/mm usage.
16 | Blocked tasks | Source had 'BLOCKED' in the Start column. Here: Blocked? = Yes, Start/Finish left blank.
17 | Status logic | Blocked? = Yes -> Blocked; else 100% -> Complete; >0% -> In Progress; else Not Started.
18 | Schedule Flag logic | Not Complete and Finish < As-of date -> OVERDUE; Finish within 7 days -> Due in 7 days; Blocked tasks show 'Blocked'; no dates -> 'No dates'.
19 | Duration | Calendar days (Finish - Start), not working days.